## PRODUCT BACKLOG
PRODUCT BACKLOG
CLIENT NAME |  | RIVERFRONT SENTRAL HOTEL
PROJECT NAME |  | GET HOTEL SYSTEM
GROUP ID |  | H21_GREEN
CODE | USER | USER STORY | PRIORITY | SPRINT # | STATUS | PRIORITY
AF_01 | CUSTOMER | As a customer, I would like to view the homepage，so that I can look how the system loking for | HIGH | 1 | COMPLETED | HIGH | HIGH PRIORITY
AF_02 | CUSTOMER | As a customer, I would like to view the service page, so that I can know what service that got at this hotel | HIGH | 1 | COMPLETED | MED | MEDIUM PRIORITY
AF_03 | CUSTOMER | As a customer, I would like to sign up, so that I need to sign up with Identification Card Number , Name , Address ,Email. | HIGH | 1 | COMPLETED | LOW | LOW PRIORITY
AF_04 | CUSTOMER | As a customer, I would like to Login, so that I can login by using Identification Card Number and Email. | HIGH | 1 | COMPLETED
AF_05 | CUSTOMER | As a customer, I would like to browse room, so that I can choose Single Room, Double Room or Family Room. | MED | 2 | COMPLETED | STATUS
AF_06 | CUSTOMER | As a customer, I would like to book a room, so that I can choose type of room, service and pay minimum Rm50 deposit. | MED | 2 | COMPLETED | PLANNING
AF_07 | CUSTOMER | As a customer, I would choose reservation date, so that I can choose Check In & Check Out Date | MED | 2 | COMPLETED | IN PROGRESS
AF_08 | CUSTOMER | As a customer, I would like to check reservation date , so that I can check my booking using Email ,Check In & Check out Date. | MED | 2 | COMPLETED | COMPLETE
AF_09 | CUSTOMER | As a customer, I would like to view Contact Us, so that I can contact when I need for help | MED | 2 | COMPLETED
AF_10 | CUSTOMER | As a customer, I would like to make payment, so that I can pay by cash. | MED | 3 | COMPLETED
AF_11 | CUSTOMER | As a customer, I would like to view Customer Statistics after login, so that I can know Booking Amount ,Total Deposit ,Amount Paid ,Service Price and Total Payment Amount | MED | 3 | COMPLETED | SPRINT #
AF_12 | CUSTOMER | As a customer, I would like to view booking receipt, so that It will tell that Your Booking Has Succeeded with your User Information | LOW | 3 | COMPLETED | 1 | SPRINT 1
AF_13 | CUSTOMER | As a customer, admin can check customer order, but no notification for customer order | LOW | 3 | COMPLETED | 2 | SPRINT 2
AF_14 | CUSTOMER | As a customer, I would like to Logout, so that It will show You Have Successfully Logged Out | LOW | 3 | COMPLETED | 3 | SPRINT 3
AF_15 | ADMIN | As an admin, I would like to Login ,so that I can login by using Admin ID and Password. | HIGH | 1 | COMPLETED
AF_16 | ADMIN | As an admin, I can view Sales Statistic, so that I can look Number of Booking ,Total Deposit Collection ,Collection Amount(From Cust) and Final Collection Amount | HIGH | 1 | COMPLETED
AF_17 | ADMIN | As an admin, I can view Number of Bookings, so that I can know how many booking per days | HIGH | 1 | COMPLETED
AF_18 | ADMIN | As an admin, I can view Total Deposit Collection, so that I can know how many that Total Deposit that have Collected | HIGH | 1 | COMPLETED
AF_19 | ADMIN | As an admin, I can view Collection Amount from customer, so that I can know how many Collection Amount From Customer. | HIGH | 1 | COMPLETED
AF_20 | ADMIN | As an admin, I can view Final Collection Amount, so that I can know how many Final Collectio Amount that earned. | MED | 1 | COMPLETED
AF_21 | ADMIN | As an admin, I can Check Customers Orders ,so that I need to Enter the Check In & Check Out Date and Choose Client's IC NO | MED | 2 | COMPLETED
AF_22 | ADMIN | As an admin, I can view the Check In Date, so that I need to choose the Check In Date | MED | 2 | COMPLETED
AF_23 | ADMIN | As an admin, I can view the Check Out Date, so that I need to choose the Check Out Date | MED | 2 | COMPLETED
AF_24 | ADMIN | As an admin, I can view the Customer Booking Report, so that I can know more detail about customer booking | MED | 2 | COMPLETED
AF_25 | ADMIN | As an admin, I can Edit Payment ,so that I can insert the Final Payment for Customer have Pay. | HIGH | 2 | COMPLETED
AF_26 | ADMIN | As an admin, I can add Room ID, so that I can Room ID for example A10 | HIGH | 2 | COMPLETED
AF_27 | ADMIN | As an admin, I can add Room Type, so that I can add Room Type which Single Bed, Double Bed and Family Room | HIGH | 2 | COMPLETED
AF_28 | ADMIN | As an admin, I can view List of Room Offered, so that It will show No, Room No ,Price ,Type ID, Room Type. | MED | 2 | COMPLETED
AF_29 | ADMIN | As an admin, I can delete List of Room Offered, I can choose to delete the room | MED | 2 | COMPLETED
AF_30 | ADMIN | As an admin, I can add Room Type ID, so that I can add Room Type ID for example J10 | MED | 2 | COMPLETED
AF_31 | ADMIN | As an admin, I can add Room Package Type, so that I can add Single Bed , Double Bed and Family Room | MED | 2 | COMPLETED
AF_32 | ADMIN | As an admin, I can delete Room Type, so that I can delete the room that no need | MED | 2 | COMPLETED
AF_33 | ADMIN | As an admin, I can view List of Registered Customers, so that I can know more about customer detail like IC NO, Name ,E-mail, Address | LOW | 3 | COMPLETED
AF_34 | ADMIN | As an admin, I can delete List of Registered Customers, so that I can delete the Registered Customer | LOW | 3 | COMPLETED
AF_35 | ADMIN | As an admin, I can Logout, so that it will show that You have successfully logged out | LOW | 3 | COMPLETED